## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | OJ_Registration001
Project Name | Online Journey
Prepared/Modified by | Role | Date of Preparation
Shubham Nigam | Tester | 2018-09-22
Reviewed by | Role | Date of Review
Harish | SME
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: PROJECT_001 |  | Project Name : Online Journey
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_LP_01 | Enter Key | Enter key in keyboard isnot acting as substitute of submit button | Detailed Description: The asset desvription text box is accepting more than 25 characters Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "click here to login" link 4. Enter valid credentials of admin to login 5. Press Enter key Actual result observed on running above steps: On executing the above mentioned steps it is observed that on pressing Enter key submit button is not clicked. | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  | ACT | Test Cycle 1 | TC_LP_02
DF_MMP_002 | Home Link | Home page link in the Manager's Menu page is not navigating to Home page. | Detailed Description: Home page link in the Manager's Menu page is not navigating to Home page. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "Click here to login" link 4. Enter valid credentials 5. Click on Submin button 6. Chick on the "Home" link Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Home page is not navigating to home page instead of navigating to home page. | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-10-24 | Siv Kumar |  |  | Test Cycle 1 | TC_MMP_01
DF_MMP_003 | View status | View status Link in the Managers Menu page is not navigating to the view status page. | Detailed Description: View status Link in the Managers Menu page is not navigating to the view status page. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "Click here to login" link 4. Enter Valid credentials 5. Click on Submit button 6. Click on "view status" link Actual result observed on running above steps: On executing the above mentioned steps it is observed that the home link is not responding instead of navigating to the home page | Coding | Google Chrome | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  |  | Test Cycle 1 | TC_MMP_004
DF_MMP_004 | Welcome text | "Welcome <user name>" is not showing in the Manager menu page. | Detailed Description: "Welcome <user name>" is not showing in the Manager menu page. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "Click here to login" link 4. Enter valid login credentials 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that "Welcome <user name>" which should be displayed at left top side of form is not displayed. | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  |  | Test Cycle 1 | TC_MMP_005
DF_MMP_005 | EMP NO | The values in dropdown box of EMP NO can't be selected by keyboard. | Detailed Description: The values in dropdown box of EMP NO of manager's raise request page is not able to selected from the keyboard when the dropdown is selected. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "Click here to login" link 4. Eter valid credentials of manager 5. Click on Submit. 6. Click on "Raise Request" link 7. Select Dropdown box of EMP NO 8. Press bottom arrow key on keyboard Actual result observed on running above steps: On executing the above mentioned steps it is observed that values in dropdown box is not changed instead of showing next value present in dropdown every time bottom arrow key is pressed. | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  |  | Test Cycle 1 | TC_MMP_008
DF_MMP_006 | EMP NO | The EMP NO is accepted even if value is not selected, instead of throwing error message | Detailed Description: The EMP NO is accepted even if value is not selected, instead of throwing error message Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "Click here to login" link 4. Enter validvredentials of manager 6. Click on Submit button 7. Click on "Raise request" link 8. Don't select EMP NO 9.Enter other valid credentials 10. Click on submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that no error message is displayed even EMP NO us not selected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-10-24 | Siva kumar |  | ACT | Test Cycle 1 | IC_MMP_13
DF_MMP_007 | Quantity text box | The text box of quantity is accepting only white spaces, instead of showing appropriate error message. | Detailed Description: The text box field of quantity in raise request page is accepting only white spaces, instead of showing an error message. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "click here to login" link 4. Enter valid credentials of manager to login 5. Click on submit button 6. Enter white spaces into quantity text 7. Enter other Valid credentials 8. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that quantity textbox is acepting white space instead of showing error. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  | ACT | Test Cycle 1 | TC_MMP_24
DF_MMP_008 | Submit button | The submit button in the raise request page is not shoing confirmation message. | Detailed Description: The submit button in the raise request page is not shoing confirmation message. after entering valid details. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "click here to login" link 4. Enter valid credentials of manager to login 5. Click on submit button 6. Enter other Valid credentials 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that confirmation message is not displayed. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  | ACT | Test Cycle 1 | TC_MMP_29
DF_AMP_009 | Asset textbox | The asset name text box ini add asset page is acepted even if it is left blank | Detailed Description: The asset name text box ini add asset page is acepted even if it is left blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "click here to login" link 4. Enter valid credentials of admin to login 5. Click on submit button 6. Click on ADD.Modify link then ADD asset link 7. Leave Asset name text box empty 8. Enter other valid details 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that asset name text box is accepting blank text, instead of displaying error message. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  | ACT | Test Cycle 1 | TC_AMP_23
DF_AMP_010 | Asset dsescription | The asset desvription text box is accepting more than 25 characters | Detailed Description: The asset desvription text box is accepting more than 25 characters Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on "click here to login" link 4. Enter valid credentials of admin to login 5. Click on submit button 6. Click on ADD.Modify link then ADD asset link 7. Wnter mare than 25 characters in asset description 8. Enter other valid details 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that asset description text box is accepting more than 25 characters, instead of displaying error message. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-10-24 | Siva Kumar |  | ACT | Test Cycle 1 | TC_AMP_30
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.